## Project Backlog
Product Backlog
# | Role | Story Summary | Story Detail | Priority | Sprint# | Status
1 | Applicant | Apply for the memebership | Applicant must be able to register for an account so that they can contribute their investment ideas | High | 1 | To be started
2 | Administrator | Evaluate the application | Admistration should be able to evaluate or scrutinize the application | High | 1 | To be started
3 | Administrator | Accept/Deny applicantion | Administration should be able to accept/deny aplicant application | High | 1 | To be started
4 | Member | Create Account | Grant access for member to create username and password | High | 1 | To be started
5 | Member | Login | Member must login to access account | High | 1 | To be started
6 | Member | Make Payment | Member must make a $1000 annual fee to fully access the website | High | 1 | To be started
7 | Member | Submit investment ideas | Members must posted 2 investment ideas on website to maintain their accounts | High | 1 | To be started
8 | Member | Pull stock prices | Member can pull stock prices to show it along with their idea (support) | High | 1 | To be started
9 | Member | Add comments | Members are able to post comments on their own and someone else's posts. | Moderate | 2 | Not Yet Started
10 | Member | Reply to comments | Members are able to reply to comments | Moderate | 2 | Not Yet Started
11 | Member | Rating the ideas | Members can rate other members' ideas on a scale of 1-5 (1 being the worst, 5 being the best) | Moderate | 2 | Not Yet Started
12 | Member | Voting on ideas | Members are able to vote for the best idea for the week | Moderate | 2 | Not Yet Started
13 | Member | Search for keywords | Members can search for specific words, comments, or people | Moderate | 2 | Not Yet Started
14 | Administrator | Removing comments | Allow adminstrators to remove irrelevant/inappropriate comments on forum posts | Moderate | 2 | Not Yet Started
15 | Administrator | Deleting ideas | Administrator can delete ideas that received rating lower than 3 stars for over 3 months | Low | 2 | Not Yet Started
16 | Administrator | Issue warning | Administrators shall issue a warning before taking more drastic actions such as revoking or suspending | Low | 3 | Not Yet Started
17 | Adminstrator | Suspend/Revoke Membership | Administrator can suspend/revoke membership if a member falls short of posting two per month, or posts ideas that get rated lowly (an average rating less than 3 for over three months) | Low | 3 | Not Yet Started

## TImeline
Sprint # | Story Points | Start Date | End Date | Status | Comments | Key:
1 | 30 | 2022-05-05 | 2022-05-12 | To be started | Applicant creates account and login after approval by admin | 1 Story Point = 8 Hours
2 | 25 | 2022-05-13 | 2022-05-19 | Not yet started | Member can post ideas, vote, comment, and use search function | Resources : 5
3 | 10 | 2022-05-20 | 2022-05-23 | Not yet started | Administrative features such as warning/suspending/removing

## Burndown
Sprint 1: Burndown
| Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6
Remaining Effort
Baseline Effort | 240 | 200 | 160 | 120 | 80 | 40 | 0